## Timeline
Estimate time for develop INCOME on R-CLIPS Management |  |  |  | Date: 09/06/2022
Task | Sub-Task | Estimate (hours) | Comment | Status
Clarifying request |  | 8
Creating package, Upload POJO Model Define Input items, output items |  | 2
Creating and defining Rule Flow |  | 4
Rule Authoring | 1. Sampling_Segmentation | 2
| 2. RCLIPS INPUT Variable logic | 16
| 3.1. Logic_Transformation_S1 | 16
| 3.2. Logic_Transformation_S2 | 16
| 3.3. Logic_Transformation_S3 | 16
| 3.4. Logic_Transformation_S4 | 16
| 4. Income_Score&Grade | 8
Testing & Fix bug |  | 16
Deploy |  | 2
| Total | 122

## Working Time
Date | 17/02/2022 | 18/02/2022 | 21/02/2022 | 22/02/2022 | 23/02/2022 | 24/02/2022 | 25/02/2022 | 28/02/2022 | 2022-01-03 | 2022-02-03 | 2022-03-03 | 2022-04-03 | 2022-06-03 | 2022-07-03 | 2022-08-03 | 2022-09-03
Working hour | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Total working hour | 128